## Backlog
ID | Category | Task | Priority (H/M/L) | Estimate time (man/day)
US-01 | Requirements & Design | Prepare SRS document | H | 2
US-02 | Requirements & Design | Maintain product backlog | H | 0.5
US-03 | Requirements & Design | Create Use Case diagram | H | 1
US-04 | Requirements & Design | Build UI prototype | M | 2
US-05 | Requirements & Design | Create 3 sequence diagrams | H | 2
US-06 | Requirements & Design | Create class diagram | H | 2
US-07 | Video Processing Core | Implement frame reading from video file | H | 2
US-08 | Video Processing Core | Detect presentation area on a frame | H | 3
US-09 | Video Processing Core | Implement Recognizer module | H | 3
US-10 | Video Processing Core | Filter duplicate frames | H | 2
US-11 | Video Processing Core | Make frame extraction rate configurable | M | 1
US-12 | Presentation Generation | Generate separate page for each unique slide | H | 2
US-13 | Presentation Generation | Generate valid Markdown/Marp output | H | 2
US-14 | Presentation Generation | Add titles and captions to slides | L | 2
US-15 | Presentation Generation | Support output theme selection | L | 1
US-16 | REST API | Upload video via REST API | H | 2
US-17 | REST API | Check processing status | H | 1
US-18 | REST API | Download generated presentation | H | 1
US-19 | REST API | Add OpenAPI/Swagger documentation | M | 1
US-20 | REST API | Validate file size and format | H | 1
US-21 | Testing | Create mocks for external dependencies | H | 1
US-22 | Testing | Write unit tests for Recognizer | H | 2
US-23 | Testing | Write integration tests for REST API | M | 2
US-24 | Testing | Prepare sample test video set | M | 0.5
US-25 | Deployment | Create Dockerfile | H | 1
US-26 | Deployment | Create docker-compose configuration | M | 1
US-27 | Deployment | Add centralized logging | M | 1
US-28 | Deployment | Clean up uploaded videos after processing | H | 0.5